## Sheet1
Cost Estimate
Project Name: Green Computing Research | Date: May 11th, 2018
Task Name | Internal Labor (By New On-boarded Members) | $/hour | Teresa (Senior System Analyst) | $/hour | James (Senior Consultant) | $/hour | Le (Green Computing Expert) | $/hour | Matt (Senior Technical Specialist) | $/hour | Internal $ Total | External Labor | $ / Hour | External $ Total | Total $ Labor | Non - Labor $ | Total Cost
WBS Categories / Hour
1. Initiating
1.1 Assigning task to team members | 24 | 100 | [8 empty] | 2400 |  |  | 0 | 2400 |  | 2400
1.2 Research on Green Computing | 56 | 100 | 8 | 90 | 11 | 90 | 13 | 90 | 7 | 80 | 9040 |  |  | 0 | 9040 |  | 9040
1.3 Kick Off meeting | 8 | 100 | [8 empty] | 800 |  |  | 0 | 800 |  | 800
1.4 Prepare business case | 32 | 100 | [8 empty] | 3200 |  |  | 0 | 3200 |  | 3200
1.5 Prepare project charter and sign | 24 | 100 | [8 empty] | 2400 |  |  | 0 | 2400 |  | 2400
1.6 Create change request form | 56 | 100 | [8 empty] | 5600 |  |  | 0 | 5600 |  | 5600
2. Planning | 0 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
2.1 Create a Project Plan | 0 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
2.1.1 Requirement tracking matrix | 40 | 100 | [8 empty] | 4000 | 15 | 200 | 3000 | 7000 |  | 7000
2.1.2 Set up a scope statement | 40 | 100 | [8 empty] | 4000 | 15 | 200 | 3000 | 7000 |  | 7000
2.1.3 List down the work breakdown structure | 40 | 100 | [8 empty] | 4000 | 15 | 200 | 3000 | 7000 |  | 7000
2.1.4 Create a Gantt Chart | 40 | 100 | [8 empty] | 4000 | 15 | 200 | 3000 | 7000 |  | 7000
2.2 Create a backup plan | 120 | 100 | [8 empty] | 12000 | 20 | 200 | 4000 | 16000 |  | 16000
3. Analysis | 0 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
3.1 Virtualization of server resources | 0 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
3.1.1 Identify the effort involved in physical server virtualization | 80 | 100 | 10 | 90 | 11 | 90 | 15 | 90 | 10 | 80 | 12040 | 15 | 200 | 3000 | 15040 |  | 15040
3.1.2 Analyze the reduction of space, energy and capital | 80 | 100 | 10 | 90 | 11 | 90 | 15 | 90 | 10 | 80 | 12040 | 15 | 200 | 3000 | 15040 |  | 15040
3.2 Disposal of electronic waste and recycling | 0 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
3.2.1 Cost analysis | 80 | 100 | [8 empty] | 8000 | 15 | 200 | 3000 | 11000 |  | 11000
3.2.2 Identify the benefits | 80 | 100 | [8 empty] | 8000 | 10 | 200 | 2000 | 10000 |  | 10000
3.2.3 Effort prediction | 88 | 100 | [8 empty] | 8800 | 20 | 200 | 4000 | 12800 |  | 12800
3.3 Data Centre and overall energy efficiency | 0 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
3.3.1 Analyze the current energy consumption | 80 | 100 | 13 | 90 | 8 | 90 | 13 | 90 | 10 | 80 | 11860 | 10 | 200 | 2000 | 13860 |  | 13860
3.3.2 Prepare energy consumption reduction plan | 80 | 100 | 13 | 90 | 8 | 90 | 13 | 90 | 10 | 80 | 11860 | 10 | 200 | 2000 | 13860 |  | 13860
3.3.3 Finalize the approach | 48 | 100 | 13 | 90 | 8 | 90 | 13 | 90 | 10 | 80 | 8660 | 10 | 200 | 2000 | 10660 |  | 10660
3.4 Development of new software to address green computing | 0 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
3.4.1 Analyze the benefits of internal use | 120 | 100 | 7 | 90 | 3 | 90 | 6 | 90 | 8 | 80 | 14080 | 15 | 200 | 3000 | 17080 |  | 17080
3.4.2 Analyze potential sale to other organizations | 128 | 100 | 5 | 90 | 5 | 90 | 5 | 90 | 5 | 80 | 14550 | 10 | 200 | 2000 | 16550 |  | 16550
4. Implementation | 0 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
4.1 Propose solution | 0 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
4.1.1 Design and code | 280 | 100 | 15 | 90 | 5 | 90 | 4 | 90 | 2 | 80 | 30320 | 10 | 200 | 2000 | 32320 |  | 32320
4.1.2 Create prototype | 200 | 100 | 15 | 90 | 5 | 90 | 9 | 90 | 4 | 80 | 22930 | 20 | 200 | 4000 | 26930 |  | 26930
4.1.3 Create software to address green computing | 280 | 100 | 15 | 90 | 6 | 90 | 11 | 90 | 3 | 80 | 31120 | 20 | 200 | 4000 | 35120 |  | 35120
4.2 Testing | 0 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
4.2.1 Create testing environment1 | 40 | 100 | 15 | 90 | 5 | 90 | 6 | 90 | 9 | 80 | 7060 |  |  | 0 | 7060 |  | 7060
4.2.2 Test the product in different cycles - development, training, UAT | 240 | 100 | 20 | 90 | 4 | 90 | 6 | 90 | 9 | 80 | 27420 | 20 | 200 | 4000 | 31420 |  | 31420
4.2.3 Track defects until resolution | 200 | 100 | 20 | 90 | 8 | 90 | 7 | 90 | 8 | 80 | 23790 | 20 | 200 | 4000 | 27790 |  | 27790
5. Performance report | 0 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
5.1 Change request analysis | 80 | 100 | [8 empty] | 8000 |  |  | 0 | 8000 |  | 8000
5.2 Requirement discussion | 80 | 100 | [8 empty] | 8000 |  |  | 0 | 8000 |  | 8000
5.3 Approve change request | 40 | 100 | [8 empty] | 4000 |  |  | 0 | 4000 |  | 4000
6. Project documentation and next release plan | 0 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
6.1 Submit Project report | 24 | 100 | [8 empty] | 2400 |  |  | 0 | 2400 |  | 2400
6.2 Present Final project report | 24 | 100 | [8 empty] | 2400 |  |  | 0 | 2400 |  | 2400
6.3 Project completion | 24 | 100 | [8 empty] | 2400 |  |  | 0 | 2400 |  | 2400
Subtotal | [10 empty] | 0 |  |  | 0 | 0 |  | 391170
Reserve | [10 empty] | 0 |  |  | 0 | 0 |  | 78234
Total | 2856 | 3300 | 179 | 1260 | 98 | 1260 | 136 | 1260 | 105 | 1120 | 331170 | 300 | 4000 | 60000 | 391170 | - | 469404

## Sheet1 (2)
Task Name | Duration | Start | Finish | Duration
Task 3.3 | 165 days | 2018-05-01 08:00 | 2018-12-17 17:00 | 1900-02-23 01:00
1. Initiating | 23 days | 2018-05-01 08:00 | 2018-05-31 17:00 | 1900-01-06 17:00
1.1 Assigning task to team members | 1 day | 2018-05-01 08:00 | 2018-05-01 17:00 | 0.375
1.2 Research on Green Computing | 7 days | 2018-05-02 08:00 | 2018-05-10 17:00 | 1900-01-01 09:00
1.3 Kick Off meeting | 2 days | 2018-05-11 08:00 | 2018-05-14 17:00 | 0.70833
1.4 Prepare business case | 5 days | 2018-05-15 08:00 | 2018-05-21 17:00 | 1899-12-31 17:00
1.5 Prepare project charter and sign | 4 days | 2018-05-22 08:00 | 2018-05-25 17:00 | 1899-12-31 09:00
1.6 Create change request form | 5 days | 2018-05-26 08:00 | 2018-05-31 17:00 | 1899-12-31 09:00
2. Planning | 9 days | 2018-06-01 08:00 | 2018-06-13 17:00 | 1900-01-02 01:00
2.1 Create a Project Plan | 8 days | 2018-06-01 08:00 | 2018-06-12 17:00 | 1900-01-01 17:00
2.1.1 Requirement tracking matrix | 2 days | 2018-06-01 08:00 | 2018-06-04 17:00 | 0.70833
2.1.2 Set up a scope statement | 2 days | 2018-06-05 08:00 | 2018-06-06 17:00 | 0.70833
2.1.3 List down the work breakdown structure | 2 days | 2018-06-07 08:00 | 2018-06-08 17:00 | 0.70833
2.1.4 Create a Gantt Chart | 2 days | 2018-06-11 08:00 | 2018-06-12 17:00 | 0.70833
2.2 Create a backup plan | 1 day | 2018-06-13 08:00 | 2018-06-13 17:00 | 0.375
3. Analysis | 40 days | 2018-06-14 08:00 | 2018-08-08 17:00 | 1900-01-12 09:00
3.1 Virtualization of server resources | 6 days | 2018-06-14 08:00 | 2018-06-21 17:00 | 1900-01-01 01:00
3.1.1 Identify the effort involved in physical server virtualization | 3 days | 2018-06-14 08:00 | 2018-06-18 17:00 | 1899-12-31 01:00
3.1.2 Analyze the reduction of space, energy and capital | 3 days | 2018-06-19 08:00 | 2018-06-21 17:00 | 1899-12-31 01:00
3.2 Disposal of electronic waste and recycling | 15 days | 2018-06-22 08:00 | 2018-07-12 17:00 | 1900-01-04 01:00
3.2.1 Cost analysis | 5 days | 2018-06-22 08:00 | 2018-06-28 17:00 | 1899-12-31 17:00
3.2.2 Identify the benefits | 5 days | 2018-06-29 08:00 | 2018-07-05 17:00 | 1899-12-31 17:00
3.2.3 Effort prediction | 5 days | 2018-07-06 08:00 | 2018-07-12 17:00 | 1899-12-31 17:00
3.3 Data Centre and overall energy efficiency | 17 days | 2018-07-13 08:00 | 2018-08-06 17:00 | 1900-01-04 17:00
3.3.1 Analyze the current energy consumption | 7 days | 2018-07-13 08:00 | 2018-07-23 17:00 | 1900-01-01 09:00
3.3.2 Prepare energy consumption reduction plan | 7 days | 2018-07-24 08:00 | 2018-08-01 17:00 | 1900-01-01 09:00
3.3.3 Finalize the approach | 3 days | 2018-08-02 08:00 | 2018-08-06 17:00 | 1899-12-31 01:00
3.4 Development of new software to address green computing | 2 days | 2018-08-07 08:00 | 2018-08-08 17:00 | 0.70833
3.4.1 Analyze the benefits of internal use | 1 day | 2018-08-07 08:00 | 2018-08-07 17:00 | 0.375
3.4.2 Analyze potential sale to other organizations | 1 day | 2018-08-08 08:00 | 2018-08-08 17:00 | 0.375
4. Implementation | 75 days | 2018-08-09 08:00 | 2018-11-21 17:00 | 1900-01-24 01:00
4.1 Propose solution | 40 days | 2018-08-09 08:00 | 2018-10-03 17:00 | 1900-01-12 09:00
4.1.1 Design and code | 10 days | 2018-08-09 08:00 | 2018-08-22 17:00 | 1900-01-02 09:00
4.1.2 Create prototype | 15 days | 2018-08-23 08:00 | 2018-09-12 17:00 | 1900-01-04 01:00
4.1.3 Create software to address green computing | 15 days | 2018-09-13 08:00 | 2018-10-03 17:00 | 1900-01-04 01:00
4.2 Testing | 35 days | 2018-10-04 08:00 | 2018-11-21 17:00 | 1900-01-10 17:00
4.2.1 Create testing environment1 | 5 days | 2018-10-04 08:00 | 2018-10-10 17:00 | 1899-12-31 17:00
4.2.2 Test the product in different cycles - development, training, UAT | 20 days | 2018-10-11 08:00 | 2018-11-07 17:00 | 1900-01-05 17:00
4.2.3 Track defects until resolution | 10 days | 2018-11-08 08:00 | 2018-11-21 17:00 | 1900-01-02 09:00
5. Performance report | 15 days | 2018-11-22 08:00 | 2018-12-12 17:00 | 1900-01-04 01:00
5.1 Change request analysis | 5 days | 2018-11-22 08:00 | 2018-11-28 17:00 | 1899-12-31 17:00
5.2 Requirement discussion | 5 days | 2018-11-29 08:00 | 2018-12-05 17:00 | 1899-12-31 17:00
5.3 Approve change request | 5 days | 2018-12-06 08:00 | 2018-12-12 17:00 | 1899-12-31 17:00
6. Project documentation and next release plan | 3 days | 2018-12-13 08:00 | 2018-12-17 17:00 | 1899-12-31 01:00
6.1 Submit Project report | 1 day | 2018-12-13 08:00 | 2018-12-13 17:00 | 0.375
6.2 Present Final project report | 1 day | 2018-12-14 08:00 | 2018-12-14 17:00 | 0.375
6.3 Project completion | 1 day | 2018-12-17 08:00 | 2018-12-17 17:00 | 0.375
Formulas:
Duration = (NETWORKDAYS([Start],[Finish])-1)*("16:00"-"8:00")+MOD([Finish],1)-MOD([Start],1)