## Sheet1
Task Name | Duration (Hours) | Resource Name | Ben (Sponsor) | Ruchika Narang (Project Manager) | Sanchit Singh (Program Manager) | Preranareddy Ananth (Outside Consultant) | Girish Garg (Systems Analyst) | Abhinay Sariswal (Green Computing Analyst) | Teresa (Senior System Analyst) | James (Senior Consultant) | Le (Green Computing Expert) | Matt (Senior Technical Specialist) | Over- sourced Labor | TTL Target Hours to Work | TTL Hours Required (By New On-boarded Members)
Project Name: Green Computing Research
WBS Categories / Hour
1. Initiating
1.1 Assigning task to team members | 24 |  |  | 24 | [9 empty] | 24 | 24
1.2 Research on Green Computing | 56 |  |  |  |  | 16 | 15 | 25 | 8 | 11 | 13 | 7 |  | 95 | 56
1.3 Kick Off meeting | 8 |  |  | 8 | [9 empty] | 8 | 8
1.4 Prepare business case | 32 |  |  | 32 | [9 empty] | 32 | 32
1.5 Prepare project charter and sign | 24 |  |  | 20 | 4 | [8 empty] | 24 | 24
1.6 Create change request form | 56 |  |  | 40 | 16 | [8 empty] | 56 | 56
2. Planning | [13 empty] | 0 | 0
2.1 Create a Project Plan | [13 empty] | 0 | 0
2.1.1 Requirement tracking matrix | 40 |  |  | 30 | 10 | [7 empty] | 15 | 55 | 40
2.1.2 Set up a scope statement | 40 |  |  | 30 | 10 | [7 empty] | 15 | 55 | 40
2.1.3 List down the work breakdown structure | 40 |  |  | 30 | 10 | [7 empty] | 15 | 55 | 40
2.1.4 Create a Gantt Chart | 40 |  |  | 20 | 20 | [7 empty] | 15 | 55 | 40
2.2 Create a backup plan | 120 |  |  | 60 | 60 | [7 empty] | 20 | 140 | 120
3. Analysis | [13 empty] | 0 | 0
3.1 Virtualization of server resources | [13 empty] | 0 | 0
3.1.1 Identify the effort involved in physical server virtualization | 80 |  |  |  |  | 27 | 26 | 27 | 2 | 11 | 15 | 10 | 15 | 133 | 80
3.1.2 Analyze the reduction of space, energy and capital | 80 |  |  |  |  | 27 | 26 | 27 | 3 | 11 | 15 | 10 | 15 | 134 | 80
3.2 Disposal of electronic waste and recycling | [13 empty] | 0 | 0
3.2.1 Cost analysis | 80 |  |  | 80 | [8 empty] | 15 | 95 | 80
3.2.2 Identify the benefits | 80 |  |  | 80 | [8 empty] | 10 | 90 | 80
3.2.3 Effort prediction | 88 |  |  | 88 | [8 empty] | 20 | 108 | 88
3.3 Data Centre and overall energy efficiency | [13 empty] | 0 | 0
3.3.1 Analyze the current energy consumption | 80 |  |  |  |  | 20 | 20 | 40 | 6 | 8 | 13 | 10 | 10 | 127 | 80
3.3.2 Prepare energy consumption reduction plan | 80 |  |  |  |  | 20 | 20 | 40 | 6 | 8 | 13 | 10 | 10 | 127 | 80
3.3.3 Finalize the approach | 48 |  |  |  |  | 20 | 10 | 18 | 6 | 8 | 13 | 10 | 10 | 95 | 48
3.4 Development of new software to address green computing | [13 empty] | 0 | 0
3.4.1 Analyze the benefits of internal use | 120 |  |  |  |  | 40 | 40 | 40 | 7 | 3 | 6 | 8 | 15 | 159 | 120
3.4.2 Analyze potential sale to other organizations | 128 |  |  |  | 30 | 32 | 34 | 32 | 5 | 5 | 5 | 5 | 10 | 158 | 128
4. Implementation | [13 empty] | 0 | 0
4.1 Propose solution | [13 empty] | 0 | 0
4.1.1 Design and code | 280 |  |  |  |  | 70 | 150 | 60 | 3 | 5 | 4 | 2 | 10 | 304 | 280
4.1.2 Create prototype | 200 |  |  |  | 30 | 50 | 80 | 40 | 7 | 5 | 9 | 4 | 20 | 245 | 200
4.1.3 Create software to address green computing | 280 |  |  |  |  | 50 | 140 | 90 | 4 | 6 | 11 | 3 | 20 | 324 | 280
4.2 Testing | [13 empty] | 0 | 0
4.2.1 Create testing environment | 40 |  |  |  |  | 10 | 20 | 10 | 4 | 5 | 6 | 9 |  | 64 | 40
4.2.2 Test the product in different cycles - development, training, UAT | 240 |  |  | 40 | 20 | 30 | 115 | 35 | 7 | 4 | 6 | 9 | 20 | 286 | 240
4.2.3 Track defects until resolution | 200 |  |  | 30 | 30 | 40 | 70 | 30 | 7 | 8 | 7 | 8 | 20 | 250 | 200
5. Performance report | [13 empty] | 0 | 0
5.1 Change request analysis | 80 |  |  | 30 | 50 | [8 empty] | 80 | 80
5.2 Requirement discussion | 80 |  |  | 50 | 30 | [8 empty] | 80 | 80
5.3 Approve change request | 40 |  |  | 20 | 20 | [8 empty] | 40 | 40
6. Project documentation and next release plan | [13 empty] | 0 | 0
6.1 Submit Project report | 24 |  |  | 17 | 7 | [8 empty] | 24 | 24
6.2 Present Final project report | 24 |  |  | 16 | 8 | [8 empty] | 24 | 24
6.3 Project completion | 24 |  |  | 24 | [9 empty] | 24 | 24
Subtotal
Reserve
Total | 2856 | [11 empty] | 300 | 3570 | 2856

## Sheet1 (2)
Task Name | Duration | Start | Finish | Duration
Task 3.3 | 165 days | 2018-05-01 08:00 | 2018-12-17 17:00 | 1900-02-23 01:00
1. Initiating | 23 days | 2018-05-01 08:00 | 2018-05-31 17:00 | 1900-01-06 17:00 | Start | Finish
1.1 Assigning task to team members | 1 day | 2018-05-01 08:00 | 2018-05-03 17:00 | 1899-12-31 01:00 | 2018-05-01 08:00 | 2018-05-03 17:00
1.2 Research on Green Computing | 7 days | 2018-05-02 08:00 | 2018-05-17 17:00 | 1900-01-03 01:00 | 2018-05-02 08:00 | 2018-05-17 17:00
1.3 Kick Off meeting | 2 days | 2018-05-11 08:00 | 2018-05-15 17:00 | 1899-12-31 01:00 | 2018-05-11 08:00 | 2018-05-15 17:00
1.4 Prepare business case | 5 days | 2018-05-15 08:00 | 2018-05-21 17:00 | 1899-12-31 17:00 | 2018-05-15 08:00 | 2018-05-21 17:00
1.5 Prepare project charter and sign | 4 days | 2018-05-22 08:00 | 2018-05-25 17:00 | 1899-12-31 09:00 | 2018-05-22 08:00 | 2018-05-25 17:00
1.6 Create change request form | 5 days | 2018-05-18 08:00 | 2018-05-31 17:00 | 1900-01-02 09:00 | 2018-05-18 08:00 | 2018-05-31 17:00
2. Planning | 9 days | 2018-06-01 08:00 | 2018-07-05 17:00 | 1900-01-07 09:00
2.1 Create a Project Plan | 8 days | 2018-06-01 08:00 | 2018-06-28 17:00 | 1900-01-05 17:00
2.1.1 Requirement tracking matrix | 2 days | 2018-06-01 08:00 | 2018-06-07 17:00 | 1899-12-31 17:00
2.1.2 Set up a scope statement | 2 days | 2018-06-08 08:00 | 2018-06-14 17:00 | 1899-12-31 17:00
2.1.3 List down the work breakdown structure | 2 days | 2018-06-15 08:00 | 2018-06-21 17:00 | 1899-12-31 17:00
2.1.4 Create a Gantt Chart | 2 days | 2018-06-22 08:00 | 2018-06-28 17:00 | 1899-12-31 17:00
2.2 Create a backup plan | 1 day | 2018-06-01 08:00 | 2018-07-05 17:00 | 1900-01-07 09:00
3. Analysis | 40 days | 2018-06-14 08:00 | 2018-08-08 17:00 | 1900-01-12 09:00
3.1 Virtualization of server resources | 6 days | 2018-06-14 08:00 | 2018-07-11 17:00 | 1900-01-05 17:00
3.1.1 Identify the effort involved in physical server virtualization | 3 days | 2018-06-14 08:00 | 2018-06-27 17:00 | 1900-01-02 09:00
3.1.2 Analyze the reduction of space, energy and capital | 3 days | 2018-06-28 08:00 | 2018-07-11 17:00 | 1900-01-02 09:00
3.2 Disposal of electronic waste and recycling | 15 days | 2018-06-22 08:00 | 2018-08-03 17:00 | 1900-01-09 09:00
3.2.1 Cost analysis | 5 days | 2018-06-22 08:00 | 2018-07-05 17:00 | 1900-01-02 09:00
3.2.2 Identify the benefits | 5 days | 2018-07-06 08:00 | 2018-07-19 17:00 | 1900-01-02 09:00
3.2.3 Effort prediction | 5 days | 2018-07-20 08:00 | 2018-08-03 17:00 | 1900-01-02 17:00
3.3 Data Centre and overall energy efficiency | 17 days | 2018-07-03 08:00 | 2018-08-07 17:00 | 1900-01-07 17:00
3.3.1 Analyze the current energy consumption | 7 days | 2018-07-03 08:00 | 2018-07-16 17:00 | 1900-01-02 09:00
3.3.2 Prepare energy consumption reduction plan | 7 days | 2018-07-17 08:00 | 2018-07-30 17:00 | 1900-01-02 09:00
3.3.3 Finalize the approach | 3 days | 2018-07-31 08:00 | 2018-08-07 17:00 | 1900-01-01 01:00
3.4 Development of new software to address green computing | 2 days | 2018-06-27 08:00 | 2018-08-08 17:00 | 1900-01-09 09:00
3.4.1 Analyze the benefits of internal use | 1 day | 2018-06-27 08:00 | 2018-07-17 17:00 | 1900-01-04 01:00
3.4.2 Analyze potential sale to other organizations | 1 day | 2018-07-18 08:00 | 2018-08-08 17:00 | 1900-01-04 09:00
4. Implementation | 75 days | 2018-08-09 08:00 | 2018-11-21 17:00 | 1900-01-24 01:00
4.1 Propose solution | 40 days | 2018-08-09 08:00 | 2018-10-03 17:00 | 1900-01-12 09:00
4.1.1 Design and code | 10 days | 2018-08-09 08:00 | 2018-09-26 17:00 | 1900-01-10 17:00
4.1.2 Create prototype | 15 days | 2018-08-17 08:00 | 2018-09-20 17:00 | 1900-01-07 09:00
4.1.3 Create software to address green computing | 15 days | 2018-08-16 08:00 | 2018-10-03 17:00 | 1900-01-10 17:00
4.2 Testing | 35 days | 2018-10-04 08:00 | 2018-11-21 17:00 | 1900-01-10 17:00
4.2.1 Create testing environment1 | 5 days | 2018-10-04 08:00 | 2018-10-10 17:00 | 1899-12-31 17:00
4.2.2 Test the product in different cycles - development, training, UAT | 20 days | 2018-10-11 08:00 | 2018-11-21 17:00 | 1900-01-09 01:00
4.2.3 Track defects until resolution | 10 days | 2018-10-11 08:00 | 2018-11-14 17:00 | 1900-01-07 09:00
5. Performance report | 15 days | 2018-11-22 08:00 | 2018-12-12 17:00 | 1900-01-04 01:00
5.1 Change request analysis | 5 days | 2018-11-22 08:00 | 2018-12-05 17:00 | 1900-01-02 09:00
5.2 Requirement discussion | 5 days | 2018-11-22 08:00 | 2018-12-05 17:00 | 1900-01-02 09:00
5.3 Approve change request | 5 days | 2018-12-06 08:00 | 2018-12-12 17:00 | 1899-12-31 17:00
6. Project documentation and next release plan | 3 days | 2018-12-13 08:00 | 2018-12-17 17:00 | 1899-12-31 01:00
6.1 Submit Project report | 1 day | 2018-12-13 08:00 | 2018-12-17 17:00 | 1899-12-31 01:00
6.2 Present Final project report | 1 day | 2018-12-13 08:00 | 2018-12-17 17:00 | 1899-12-31 01:00
6.3 Project completion | 1 day | 2018-12-13 08:00 | 2018-12-17 17:00 | 1899-12-31 01:00
Formulas:
Duration = (NETWORKDAYS([Start],[Finish])-1)*("16:00"-"8:00")+MOD([Finish],1)-MOD([Start],1)