## Sheet1
Cost Baseline
Project Name: Green Computing Research | Date: May 11th, 2018
Task Name | Month | [6 empty] | Total Cost
| 1 | 2 | 3 | 4 | 5 | 6 | 7
WBS Categories / Hour
1. Initiating
1.1 Assigning task to team members | 2400 | [6 empty] | 2400
1.2 Research on Green Computing | 9040 | [6 empty] | 9040
1.3 Kick Off meeting | 800 | [6 empty] | 800
1.4 Prepare business case | 3200 | [6 empty] | 3200
1.5 Prepare project charter and sign | 2400 | [6 empty] | 2400
1.6 Create change request form | 5600 | [6 empty] | 5600
2. Planning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 Create a Project Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1 Requirement tracking matrix | 3500 | 3500 | [5 empty] | 7000
2.1.2 Set up a scope statement | 3500 | 3500 | [5 empty] | 7000
2.1.3 List down the work breakdown structure | 3500 | 3500 | [5 empty] | 7000
2.1.4 Create a Gantt Chart | 3500 | 3500 | [5 empty] | 7000
2.2 Create a backup plan | 8000 | 8000 | [5 empty] | 16000
3. Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1 Virtualization of server resources | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.1 Identify the effort involved in physical server virtualization |  | 8000 | 7040 |  |  |  |  | 15040
3.1.2 Analyze the reduction of space, energy and capital |  | 8000 | 7040 |  |  |  |  | 15040
3.2 Disposal of electronic waste and recycling |  | 0 | 0 | 0 |  |  |  | 0
3.2.1 Cost analysis |  | 1650 | 8000 | 1350 |  |  |  | 11000
3.2.2 Identify the benefits |  | 1650 | 7000 | 1350 |  |  |  | 10000
3.2.3 Effort prediction |  | 1650 | 8000 | 3150 |  |  |  | 12800
3.3 Data Centre and overall energy efficiency |  | 0 | 0 | 0 |  |  |  | 0
3.3.1 Analyze the current energy consumption |  |  | 8200 | 5660 |  |  |  | 13860
3.3.2 Prepare energy consumption reduction plan |  |  | 8200 | 5660 |  |  |  | 13860
3.3.3 Finalize the approach |  |  | 5300 | 5360 |  |  |  | 10660
3.4 Development of new software to address green computing |  | 0 | 0 | 0 |  |  |  | 0
3.4.1 Analyze the benefits of internal use |  | 1100 | 12500 | 3480 |  |  |  | 17080
3.4.2 Analyze potential sale to other organizations |  | 1100 | 12100 | 3350 |  |  |  | 16550
4. Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1 Propose solution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.1 Design and code |  |  |  | 24500 | 7820 |  |  | 32320
4.1.2 Create prototype |  |  |  | 23200 | 3730 |  |  | 26930
4.1.3 Create software to address green computing |  |  |  | 27300 | 7820 |  |  | 35120
4.2 Testing |  |  |  | 0 | 0 | 0 | 0 | 0
4.2.1 Create testing environment1 |  |  |  |  | 2600 | 4460 |  | 7060
4.2.2 Test the product in different cycles - development, training, UAT |  |  |  |  | 27600 | 3820 |  | 31420
4.2.3 Track defects until resolution |  |  |  |  | 24800 | 2990 |  | 27790
5. Performance report | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1 Change request analysis | [5 empty] | 2300 | 5700 | 8000
5.2 Requirement discussion | [5 empty] | 2300 | 5700 | 8000
5.3 Approve change request | [5 empty] | 1200 | 2800 | 4000
6. Project documentation and next release plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1 Submit Project report | [6 empty] | 2400 | 2400
6.2 Present Final project report | [6 empty] | 2400 | 2400
6.3 Project completion | [6 empty] | 2400 | 2400
Subtotal | 45440 | 45150 | 83380 | 104360 | 74370 | 17070 | 21400 | 391170
Reserve | 9088 | 9030 | 16676 | 20872 | 14874 | 3414 | 4280 | 78234
Total | [7 empty] | 469404

## Sheet1 (2)
Task Name | Duration | Start | Finish | Duration
Task 3.3 | 165 days | 2018-05-01 08:00 | 2018-12-17 17:00 | 1900-02-23 01:00
1. Initiating | 23 days | 2018-05-01 08:00 | 2018-05-31 17:00 | 1900-01-06 17:00
1.1 Assigning task to team members | 1 day | 2018-05-01 08:00 | 2018-05-01 17:00 | 0.375
1.2 Research on Green Computing | 7 days | 2018-05-02 08:00 | 2018-05-10 17:00 | 1900-01-01 09:00
1.3 Kick Off meeting | 2 days | 2018-05-11 08:00 | 2018-05-14 17:00 | 0.70833
1.4 Prepare business case | 5 days | 2018-05-15 08:00 | 2018-05-21 17:00 | 1899-12-31 17:00
1.5 Prepare project charter and sign | 4 days | 2018-05-22 08:00 | 2018-05-25 17:00 | 1899-12-31 09:00
1.6 Create change request form | 5 days | 2018-05-26 08:00 | 2018-05-31 17:00 | 1899-12-31 09:00
2. Planning | 9 days | 2018-06-01 08:00 | 2018-06-13 17:00 | 1900-01-02 01:00
2.1 Create a Project Plan | 8 days | 2018-06-01 08:00 | 2018-06-12 17:00 | 1900-01-01 17:00
2.1.1 Requirement tracking matrix | 2 days | 2018-06-01 08:00 | 2018-06-04 17:00 | 0.70833
2.1.2 Set up a scope statement | 2 days | 2018-06-05 08:00 | 2018-06-06 17:00 | 0.70833
2.1.3 List down the work breakdown structure | 2 days | 2018-06-07 08:00 | 2018-06-08 17:00 | 0.70833
2.1.4 Create a Gantt Chart | 2 days | 2018-06-11 08:00 | 2018-06-12 17:00 | 0.70833
2.2 Create a backup plan | 1 day | 2018-06-13 08:00 | 2018-06-13 17:00 | 0.375
3. Analysis | 40 days | 2018-06-14 08:00 | 2018-08-08 17:00 | 1900-01-12 09:00
3.1 Virtualization of server resources | 6 days | 2018-06-14 08:00 | 2018-06-21 17:00 | 1900-01-01 01:00
3.1.1 Identify the effort involved in physical server virtualization | 3 days | 2018-06-14 08:00 | 2018-06-18 17:00 | 1899-12-31 01:00
3.1.2 Analyze the reduction of space, energy and capital | 3 days | 2018-06-19 08:00 | 2018-06-21 17:00 | 1899-12-31 01:00
3.2 Disposal of electronic waste and recycling | 15 days | 2018-06-22 08:00 | 2018-07-12 17:00 | 1900-01-04 01:00
3.2.1 Cost analysis | 5 days | 2018-06-22 08:00 | 2018-06-28 17:00 | 1899-12-31 17:00
3.2.2 Identify the benefits | 5 days | 2018-06-29 08:00 | 2018-07-05 17:00 | 1899-12-31 17:00
3.2.3 Effort prediction | 5 days | 2018-07-06 08:00 | 2018-07-12 17:00 | 1899-12-31 17:00
3.3 Data Centre and overall energy efficiency | 17 days | 2018-07-13 08:00 | 2018-08-06 17:00 | 1900-01-04 17:00
3.3.1 Analyze the current energy consumption | 7 days | 2018-07-13 08:00 | 2018-07-23 17:00 | 1900-01-01 09:00
3.3.2 Prepare energy consumption reduction plan | 7 days | 2018-07-24 08:00 | 2018-08-01 17:00 | 1900-01-01 09:00
3.3.3 Finalize the approach | 3 days | 2018-08-02 08:00 | 2018-08-06 17:00 | 1899-12-31 01:00
3.4 Development of new software to address green computing | 2 days | 2018-08-07 08:00 | 2018-08-08 17:00 | 0.70833
3.4.1 Analyze the benefits of internal use | 1 day | 2018-08-07 08:00 | 2018-08-07 17:00 | 0.375
3.4.2 Analyze potential sale to other organizations | 1 day | 2018-08-08 08:00 | 2018-08-08 17:00 | 0.375
4. Implementation | 75 days | 2018-08-09 08:00 | 2018-11-21 17:00 | 1900-01-24 01:00
4.1 Propose solution | 40 days | 2018-08-09 08:00 | 2018-10-03 17:00 | 1900-01-12 09:00
4.1.1 Design and code | 10 days | 2018-08-09 08:00 | 2018-08-22 17:00 | 1900-01-02 09:00
4.1.2 Create prototype | 15 days | 2018-08-23 08:00 | 2018-09-12 17:00 | 1900-01-04 01:00
4.1.3 Create software to address green computing | 15 days | 2018-09-13 08:00 | 2018-10-03 17:00 | 1900-01-04 01:00
4.2 Testing | 35 days | 2018-10-04 08:00 | 2018-11-21 17:00 | 1900-01-10 17:00
4.2.1 Create testing environment1 | 5 days | 2018-10-04 08:00 | 2018-10-10 17:00 | 1899-12-31 17:00
4.2.2 Test the product in different cycles - development, training, UAT | 20 days | 2018-10-11 08:00 | 2018-11-07 17:00 | 1900-01-05 17:00
4.2.3 Track defects until resolution | 10 days | 2018-11-08 08:00 | 2018-11-21 17:00 | 1900-01-02 09:00
5. Performance report | 15 days | 2018-11-22 08:00 | 2018-12-12 17:00 | 1900-01-04 01:00
5.1 Change request analysis | 5 days | 2018-11-22 08:00 | 2018-11-28 17:00 | 1899-12-31 17:00
5.2 Requirement discussion | 5 days | 2018-11-29 08:00 | 2018-12-05 17:00 | 1899-12-31 17:00
5.3 Approve change request | 5 days | 2018-12-06 08:00 | 2018-12-12 17:00 | 1899-12-31 17:00
6. Project documentation and next release plan | 3 days | 2018-12-13 08:00 | 2018-12-17 17:00 | 1899-12-31 01:00
6.1 Submit Project report | 1 day | 2018-12-13 08:00 | 2018-12-13 17:00 | 0.375
6.2 Present Final project report | 1 day | 2018-12-14 08:00 | 2018-12-14 17:00 | 0.375
6.3 Project completion | 1 day | 2018-12-17 08:00 | 2018-12-17 17:00 | 0.375
Formulas:
Duration = (NETWORKDAYS([Start],[Finish])-1)*("16:00"-"8:00")+MOD([Finish],1)-MOD([Start],1)